## Sheet1
DocuDB | Task | Owner | Start Date | End Date | Duration (days)
🔐 Feature 1: User Authentication & Management
User Story 1.1: As a user, I want the system to automatically detect my role (Admin/User) so I’m redirected to the correct dashboard. | Acceptance Criteria: • No manual login required. • Role is identified on entry. • Admin → Admin Dashboard, User → User Dashboard.
| Implement role-checking logic | Backend
| Setup auto-redirects for Admin/User | Backend
| Design role-specific dashboards | UI/UX
📂 Feature 2: Document & Folder Management
User Story 2.1: As a user, I want to upload and organize documents in folders so I can store them properly. | Acceptance Criteria: • Upload supports PDF, Word, Excel, images. • Files can be placed inside folders. • Upload progress visible.
| Design file/folder UI | UI/UX
| Implement file upload API | Backend
| Connect frontend upload with backend | Frontend
User Story 2.2: As a user, I want to delete, rename, and move documents so I can manage them easily. | Acceptance Criteria: • Users can delete/rename/move files & folders. • Changes reflect immediately.
| Implement rename/delete logic | Backend
| Update UI for folder/file actions | Frontend
| Add confirmation dialogs | Backend
🔗 Feature 3: Document Sharing & Permissions
User Story 3.1: As a user, I want to share a document with another user so they can view or edit it. | Acceptance Criteria: • Permissions: Read, Write, Full. • Shared users can only access assigned documents.
| Design sharing UI with permissions | UI/UX
| Implement permission logic in backend | Backend
| Connect UI to backend | Frontend
🛠 Feature 4: Search & Filters
User Story 4.1: As a user, I want to search documents by name/type/date so I can find them quickly. | Acceptance Criteria: • Search is case-insensitive. • Results update in real-time.
| Design search bar UI | UI/UX
| Implement backend search API | Backend
| Integrate search results in UI | Frontend
👨‍💼 Feature 5: Admin User & Role Management
User Story 5.1: As an Admin, I want to manage user accounts so I can control who has access. | Acceptance Criteria: • Admin can view, add, edit, deactivate users. • User list shows role (Admin/User).
| Design user management UI | UI/UX
| Implement backend logic for user roles | Backend
| Add audit log for user changes | Backend
User Story 5.2: As an Admin, I want to assign and change user roles so I can control system privileges. | Acceptance Criteria: • Roles: Admin / User. • Role change updates in real-time.
| Implement role update function | Backend
| Update UI with role dropdown | Frontend
📊 Feature 6: System Monitoring & Logs
User Story 6.1: As an Admin, I want to view system activity logs so I can track usage. | Acceptance Criteria: • Logs include uploads, deletions, sharing, role changes. • Logs show user, action, timestamp.
| Implement backend logging mechanism | Backend
| Create admin log viewer UI | UI/UX
| Add filter/search for logs | Frontend
User Story 6.2: As an Admin, I want to export logs so I can keep audit records. | Acceptance Criteria: • Logs exportable to CSV/PDF.
| Add export function | Backend